## Sheet1
When: 19/05/2025 02:00 PM |  | Who: Brent Forge & Ben O'Hara | Application: Timeups Website
Note: please make sure you fill all information related to your project below and convert/include link to Wiki Or readme.md (GitHub)
ID | Scenario Title | Status | Scenario | Remarks
1 | Home Page | Failed | The website opens on the homepage. This pages shows links to other pages and images of the watches that are available.The hero image of the page scrolls horizontallly to show 3 different sets of images. | The links on the menu bar work and navigate correctly to the appropriate pages. The Contact button on the page beneath the images does not work. The social media links do not function. Clicking on the image of a particular watch does not navigate to a page showing more details about that item.
2 | Contact | Pass | If the user of the site wishes to contact the owner, then, when they click on the "Contact Us" option on the header, they should be taken to a page containing the owner's contact details. | Selecting "Contact Us" takes the user to a page where they can fill in a form with their name, email, phone number and the message that they wish to send to the owner. However, the text field for the 'Message' is the same as the other fields, when it really should be a larger text field.
3 | Products | Pass | When the user selects the "Products" option on the header, assuming that they are looking for information about the products offered, they should get access to all of the products that Timups offers. | Selecting "Watches" takes the user to a page that displays all of the smartwatches Timups has to offer, complete with display images and prices. However, selecting any of these watches, or the 'View All' button, solely refreshes the page.
4 | Orders | Pass | When the user selects the "Orders" page on the header bar, they should be taken to a page which shows the details of all of the orders which they have placed on the site. There are also buttons to 'view order' and to 'track shipment.' | None of the links or buttons are functioning. The page is well laid out and shows the order number and the details of the products ordered with buttons to 'buy it again' and 'request a return.'
5 | About | Pass | If the user of the site selects the "About" option on the header, they should get access to a webpage containing information about the company Timups. We assume that the user's intent was to find out more information about Timups. | Upon selecting the 'About' option, the user is dirrected to a page showing more information about Timups. However, as of now, the text is purely placeholder and the 'Read More' button does nothing but refresh the page.
6 | Footer | Failed | The links and buttons in the sites footer should redirect to wherever their name or apperance may suggest. E.g: An Instagram symbol should redirect to their Instagram page. | All of the links and buttons in the footer solely refresh the page. The 'Subscribe' button has no feedback to verify that it has worked. The Google Maps box in the bottom right hand corner of the website is not functioning.
7 | Header | Failed | All of the options and buttons present on the header should redirect to their respective page. | Although the options ('About', 'Orders', etc) all direct to the correct pages, the three buttons on the side don't direct to anything, instead just refreshing the page.