## Sheet1
Website
BnB Tech | [5 empty] | Legend: | Milestone | Low risk | Med risk | High risk | On Track | Unaltered
Ben O'Hara & Brent Forge
Project Start Date: | 2025-02-17 |  |  |  |  | February | [14 empty] | March | [27 empty] | April | [28 empty] | May
[6 empty] | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Milestone description | Category | Assigned to | Progress | Start | Hours | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
ITERATION 1
Create Stakeholder Register | High Risk | Ben & Brent | 100% | 2025-02-17 | 2 | bar: T
Create Group Meeting Report (1) | Med Risk | Ben & Brent | 100% | 2025-02-17 | 0.5 | bar: T
Design 2 Personas | Med Risk | Ben & Brent | 100% | 2025-03-03 | 2 | bar: F
Review Personas | Low Risk | Ben & Brent | 100% | 2025-03-04 | 0.1 | bar: S
Create Github Repository | High Risk | Brent | 100% | 2025-03-04 | 2 | bar: S
Create README File (1) | Med Risk | Brent | 100% | 2025-03-04 | 0.1 | bar: S
Create Group Meeting Report (2) | Med Risk | Ben & Brent | 100% | 2025-03-04 | 0.5 | bar: S
Create Progress Report | Milestone | Ben & Brent | 100% | 2025-03-17 | 0.2 | bar: F
ITERATION 2
Create Resource Table | Med Risk | Ben & Brent | 100% | 2025-03-25 | 2 | bar: S
Create Gantt Chart | Med Risk | Ben | 80% | 2025-04-01 | 2 | bar: W
Create README File (2) | Med Risk | Ben | 100% | 2025-04-01 | 0.1 | bar: W
Create Group Meeting Report (3) | Med Risk | Brent | 100% | 2025-04-01 | 0.5 | bar: W
Impliment Github Features | Unaltered | Ben & Brent | 0% | 2025-04-07 | 0.2 | bar: T
ITERATION 3
Create Group Meeting Report (4) | Unaltered | Ben & Brent | 0% | 2025-04-15 | 0.5 | bar: W
Complete Risk Register | Unaltered | Ben & Brent | 0% | 2025-04-08 | 2 | bar: W
Integrate Code, Push to Github and Review Integration | Unaltered | Ben & Brent | 0% | 2025-04-22 | 2 | bar: W
Complete User Acceptance Testing | Unaltered | Ben & Brent | 0% | 2025-04-29 | 2 | bar: W
Publish Website | Unaltered | Ben & Brent | 0% | 2025-05-18 | 0.1 | bar: S